## Detailed Gantt Chart and Plan
|  | PLANNED |  |  |  | ACTUAL
| Tasks | Start Date | Duration (Days) | End Date | Responsible | Start | Duration | End
Research Topics | Research | 2014-02-15 | 40 | 2014-03-27 | All
| DB Design (to store SVN log data) | 2014-02-10 | 14 |  | SA, VR
| SVN Log parse, extract, import | 2014-02-16 | 10 |  | SA, TR
Programming | Learn about Eclipse Plugins | 2014-02-18 | 12 |  | TR, AG
| Design | 2014-02-27 | 5 |  | AG
| Implement simple metric | 2014-03-01 | 10 |  | TR, AG
| Implement complex metrics | 2014-03-10 | 15 |  | TR, AG
Testing | Test data creation | 2014-03-02 | 15 | 2014-03-17 | VR, AG
| Test code implementation | 2014-03-04 | 15 | 2014-03-19 | AG
| Regression testing | 2014-03-10 | 10 | 2014-03-20 | All
Measurement | Collect data for Ant (Measure) | 2014-03-20 | 5 |  | SA, TR
| Analyze Metrics | 2014-03-23 | 10 |  | SA
Final Report | Report - Introduction | 2014-03-08 | 7 |  | AG
| Report - Previous work | 2014-03-15 | 10 |  | AG, VR
| Report - Results (statistics) | 2014-03-23 | 15 |  | SA, AG
| Report - Analysis | 2014-04-04 | 8 |  | SA, TR
| Report - Conclusion and abstract | 2014-04-11 | 5 |  | AG
Formulas:
End Date = [Start Date]+[Duration (Days)]